# Agenda

Go SOLAR Florida Team Leader Update Meeting

July 24, 2014

Broward County Government Center West, PLCP Room 1303A

Welcome and Roll Call

* Cathy Randazzo, Zoning and Planning
* Matt Anderson, Marketing
* Michael Huneke, Plans and Permitting
* Andrea Bousquet, IT
* Icilda Humes, Administration
* Jason Liechty, Finance Action Plan

Updates:

* Finance Action Plan
* Marketing
* Contracts
* Plans and Permitting
* Timesheets

Discussion on Legislative Matters

Next Meeting August 28, 2014 at 2pm in Room PLCP 1303A.

Important Project Dates

Project Time Frame:

1. Budget Period One: 9-12-13 to 3-31-15

| **Due Date** | **Team Leader** | **Deliverable** | **Status** |
| --- | --- | --- | --- |
| Q1 | Kay | Minutes of the kick-off meeting | Completed |
| Q1 | Kay | Go SOLAR-Florida Charter documenting key players, and other administrative elements of the governance structure | Completed |
| Q1 | Kay & Cathy | Executed inter-county interlocal agreements | Pending FSEC and FAU contracts |
| Q1 | Cathy | Executed partner agreements with FSEC and FAU | At County Attorney’s Office |
| Q3 | Mike | Executed county-city interlocal agreements |  |
| Q4 | Mike | Updated video of training webinar posted to www.broward.org/gogreen/gosolar |  |
| Q4 | Mike | New partner cities will be operational on gosolar.broward.org |  |
| Q5 | Kay | Weblink to the implemented FSEC online electronic plans storehouse |  |
| Q6 | Kay | Design plans for or weblinks to each partner county’s ePermit solution |  |
| Q6 | Kay | Completion of FSEC training in the use of their online electronic plans storehouse, documented by a video of a live webinar training posted online and instructions for the use of the storehouse |  |
| Q4 | Cathy | An inter-county Planning and Zoning Best Management Practices and model zoning ordinance |  |
| Q6 | Cathy | Formal adoption of the zoning ordinance language by all permitting jurisdictions |  |
| Q4 | Jennifer | Web link to the Florida Solar Financing Action Plan (GSFAP), posted online |  |
| Q4 | Jennifer | Web link to recommended proclamation language supporting the GSFAP, posted online |  |
| Q6 | Jennifer | Web link to all executed proclamations from all Florida Counties in support of the GSFAP, posted online |  |
| Q2 | Matt | Go SOLAR-Florida Marketing Plan |  |
| Q6 | Matt | Conduct at least four workshops on solar rights |  |
| Q6 | Kay/Matt | Conduct one workshop between partner county power companies to promote  collaboration on consistent, statewide net metering and interconnection standards |  |
| Q6 | Matt | Complete the 2nd Annual Go SOLAR Fest |  |
| Q6 | Matt/Jennifer | Solar Financing Marketing Campaign |  |
| 3-31-15 | Kay | **Go/No Go Decision Point**  DOE will make a determination to proceed with funding for the next Budget Performance period (BP2) based predominately upon the successful completion of 85% of the subtasks and deliverables for BP1 described in the approved SOPO. Other budgetary and programmatic constraints may apply. |  |
| Q9 | Kay | Train building officials and inspectors from new jurisdictions on how to use the Go SOLAR Online Permitting System. |  |
| Q9 | Kay | Monitor and evaluate the performance of Go SOLAR systems, and refine the permitting solution, as needed, based on customer feedback |  |
| Q9 | Kay | Web links to all ePermit solutions implemented within each partner county |  |
| Q10 | Matt | Conduct at least two workshops on solar rights |  |
| Q10 | Kay | Seek audience with the Florida Public Service Commission to presents results of Go-SOLAR Florida |  |
| Q10 | Jennifer/Matt | Conduct one state-wide financial options workshop |  |
| Q10 | Matt | Post all marketing and outreach materials online |  |
| Q10 | Matt | Report on success of Go SOLAR-Florida Marketing Plan, including the estimated total number of customer touch points |  |
| Q10 | Matt | The 3rd Annual Go SOLAR Fest will be conducted within a partner location, to include a qualitative/quantitative analysis of how Go SOLAR-Florida has impacted the solar market in participating jurisdictions, and plans for the future. Impact metrics will be similar to those defined in Task 6. |  |
| Q10 + 90 days | Kay | Reports and other deliverables will be provided to DOE in accordance with the Federal Assistance Reporting Checklist. |  |

|  |  |
| --- | --- |
| **Quarter** | **Dates** |
| 1 | 9-30-13 to 12-31-13 |
| 2 | 1-1-14 to 3-31-14 |
| 3 | 4-4-14 to 6-31-14 |
| 4 | 7-1-14 to 9-30-14 |
| 5 | 10-1-14 to 12-31-14 |
| 6 | 1-1-15 to 3-31-15 |
| 7 | 4-1-15 to 6-31-15 |
| 8 | 7-1-15 to 9-30-15 |
| 9 | 10-1-15 to 12-31-15 |
| 10 | 1-1-16 to 3-31-16 |