## POR Construction
PMO PLAN OF RECORD - Surtax Municipal Capital Project - CONSTRUCTION
Municipality and ILA/PFA Project Manager: | [8 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project ID and Description:
Project Start Date: | [7 empty] | 2021-10-07 |  | October | [27 empty] | November
Scrolling Increment: | [7 empty] | 0 | time axis 2021-10-07 to 2021-12-01
Milestone Description | Milestones | Milestones2 | Progress % Complete | Start | Finish | Duration (Days) | Status | Assessed Risk | Comments | time axis 2021-10-07 to 2021-12-01
0
PHASE 1 - PRECONSTRUCTION
Project Start - NTP |  |  | 100% | 2021-10-07 | 2021-10-08 | 1 | Complete | On Track
Permit Approvals |  |  | 100% | 2021-10-08 | 2021-10-18 | 10 | Complete | On Track
Shop Drawing Approvals |  |  | 50% | 2021-10-10 | 2021-10-31 | 21 | In Progress | On Track
Sample /Material Approvals |  |  | 25% | 2021-10-14 | 2021-10-19 | 5 | In Progress | On Track
Utility Clearances | Yes |  | 75% | 2021-10-21 | 2021-11-04 | 14 | In Progress | Low Risk | FPL Delay
PHASE 2 -EB CONSTRUCTION
Mobilization (Clear & Grub) |  | Milestone | 60% | 2021-10-13 | 2021-10-27 | 14 | In Progress | On Track
Drainage Installation | Yes |  | 50% | 2021-10-15 | 2021-11-05 | 21 | In Progress | Delayed | Redesign flowline
Structures - (Frame, Form, Rebar, Repair, Rehab) | Yes | Milestone | 33% | 2021-10-20 | 2021-11-14 | 25 | In Progress | On Track
Concrete - (Prep, Pour, Cure) |  |  |  | 2021-10-22 | 2021-11-05 | 14 | Not Started | On Track
Signalization, Mast Arms | Yes | Milestone |  | 2021-10-23 | 2021-11-17 | 25 | Not Started | High Risk | Fabrication Delay
PHASE 3 -WB CONSTRUCTION
Conduit, Electrical & Testing | Yes | Milestone |  | 2021-10-22 | 2021-11-08 | 17 | Not Started | Med Risk | Underground Conflict
Lighting (Poles & Fixtures) |  |  |  | 2021-10-25 | 2021-11-04 | 10 | Not Started | Delayed | Above ground Conflict
Mill & Resurface Asphalt (Mill, Prime, Base, SC, FC) | Yes | Milestone |  | 2021-11-09 | 2021-11-23 | 14 | Not Started | On Track
Signage & Pavement Marking (Thermoplastic) |  | Milestone |  | 2021-11-13 | 2021-11-23 | 10 | Not Started | On Track
Landscape / Irrigation |  |  |  | 2021-10-21 | 2021-11-04 | 14 | Not Started | On Track
CLOSE-OUT
Substantial Completion Inspection Punchlist |  |  |  | 2021-11-16 | 2021-11-30 | 14 | Not Started | Low Risk | Rework
Final Completion Inspection Punchlist | Yes | Milestone |  | 2021-11-30 | 2021-12-01 | 1 | Not Started | On Track
Project End - Final Acceptance (Notify BC PMO) |  |  |  | 2021-12-01 | 2021-12-02 | 1 | Not Started | On Track
To add more data, Insert new rows ABOVE this one
EXAMPLE

## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.